## About
Gap & Action Tracker
Mumbai University
Organisation | Mumbai University
As of | 8 October 2026
Version | 3
Generated | 8 October 2026, 10:20 IST by Registrar (DPDP Programme Owner)
Report | Every gap and action from the assessment and the register, as a working file.
About this export
This report is a DPDP readiness and assessment output based on information, responses and evidence made available during the assessment. It is not a final legal opinion, statutory certification or guarantee of compliance. Final legal interpretation, policy approval and contractual sign-off should be reviewed by authorised legal counsel.
Notes
Actions: one row per remediation action, from the assessments and the processing register, labelled by source.
Gaps: one row per gap, with how many of its actions are still owed.
Penalty heads are those the gap counts against directly under the TrustStack exposure model; the window and Overdue are measured from today's date in India.
Every value is as stored when the file was generated; no cell holds a formula.

## Actions
Source | Assessment or record | Area or register rule | Action | Severity | Priority | Owner | Status | Due date | Roadmap window | Overdue | Gap | Penalty heads | Artefacts attached | Accepted artefacts | Closed on | Closed by | Closed on the basis of | Notes
Assessment | Mumbai University DPDP Compass Baseline | Governance, accountability and DPDP ownership | Nominate DPDP owner and publish internal responsibility note. | Low | P3 | Unassigned | Open |  | Next assessment cycle | No | Open | Enabling control | 0 | 0
Processing register | Online admission application | ROPA-001 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-001) | Critical | P0 | Controller of Examinations (Department Owner) | Open | 2026-09-26 | Overdue | Yes | Open | Head 3 | 0 | 0
Processing register | Online admission application | ROPA-001 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-001) | Critical | P0 | Controller of Examinations (Department Owner) | Open | 2026-10-05 | Overdue | Yes | Open | Head 3 | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-002) | Critical | P0 | Controller of Examinations (Department Owner) | Open | 2026-10-17 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-002) | Critical | P0 | Controller of Examinations (Department Owner) | Open | 2026-11-02 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-003) | Critical | P0 | Controller of Examinations (Department Owner) | Open | 2026-11-25 | 31–60 days | No | Open | Head 3 | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-003) | Critical | P0 | Controller of Examinations (Department Owner) | Open | 2027-02-05 | After 90 days | No | Open | Head 3 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-004) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-004) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-006) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-006) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-007) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-007) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | AI student chatbot | ROPA-008 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-008) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | AI student chatbot | ROPA-008 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-008) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · No verifiable parental consent | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. (ROPA-009) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · Children may be tracked or targeted | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. (ROPA-009) | Critical | P0 | Unassigned | Open | 2026-11-05 | Next 30 days | No | Open | Head 3 | 0 | 0
Processing register | Online admission application | ROPA-001 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-001) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Online admission application | ROPA-001 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-001) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Online admission application | ROPA-001 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-001) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-002) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-002) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-002) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-003) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-003) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-003) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-004) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | LMS learning activity | ROPA-004 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-004) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · Processor without a valid contract | Put a contract with DPDP and security clauses in place with each linked Data Processor (s.8(2), Rule 6(1)(f)). (ROPA-004) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 1, Head 7 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-004) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · AI processing not reviewed | Review the AI or automated processing and approve the record. (ROPA-004) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 4 | 0 | 0
Processing register | HR payroll and employee records | ROPA-005 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-005) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | HR payroll and employee records | ROPA-005 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-005) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-006) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-006) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-006) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-007) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-007) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-007) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | AI student chatbot | ROPA-008 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-008) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | AI student chatbot | ROPA-008 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-008) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | AI student chatbot | ROPA-008 · Retention or erasure undecided | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). (ROPA-008) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | AI student chatbot | ROPA-008 · AI processing not reviewed | Review the AI or automated processing and approve the record. (ROPA-008) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 4 | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-009) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-009) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Alumni communications | ROPA-010 · No owner | Assign a named owner who is accountable for this processing activity. (ROPA-010) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Enabling control | 0 | 0
Processing register | Alumni communications | ROPA-010 · Purpose or lawful ground undecided | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. (ROPA-010) | High | P1 | Unassigned | Open | 2026-12-05 | 31–60 days | No | Open | Head 7 | 0 | 0
Processing register | Online admission application | ROPA-001 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-001) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Online admission application | ROPA-001 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-001) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Online admission application | ROPA-001 · Review overdue | Review the record and set its next review date. (ROPA-001) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-002) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Consent capture not recorded | Record how consent is captured and how it can be withdrawn as easily as it was given. (ROPA-002) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 7 | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-002) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Examination registration and result processing | ROPA-002 · Review overdue | Review the record and set its next review date. (ROPA-002) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-003) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-003) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Review overdue | Review the record and set its next review date. (ROPA-003) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | LMS learning activity | ROPA-004 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-004) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | LMS learning activity | ROPA-004 · Review overdue | Review the record and set its next review date. (ROPA-004) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | HR payroll and employee records | ROPA-005 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-005) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | HR payroll and employee records | ROPA-005 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-005) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | HR payroll and employee records | ROPA-005 · Review overdue | Review the record and set its next review date. (ROPA-005) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-006) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-006) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Scholarship and concession processing | ROPA-006 · Review overdue | Review the record and set its next review date. (ROPA-006) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-007) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-007) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Affiliated college data exchange | ROPA-007 · Review overdue | Review the record and set its next review date. (ROPA-007) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | AI student chatbot | ROPA-008 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-008) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | AI student chatbot | ROPA-008 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-008) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | AI student chatbot | ROPA-008 · Review overdue | Review the record and set its next review date. (ROPA-008) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-009) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-009) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Event and webinar registration | ROPA-009 · Review overdue | Review the record and set its next review date. (ROPA-009) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Alumni communications | ROPA-010 · Vendor not mapped | Link the Data Processors involved to the vendor register. (ROPA-010) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0
Processing register | Alumni communications | ROPA-010 · Rule 6 minimum safeguards not confirmed | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. (ROPA-010) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Head 1 | 0 | 0
Processing register | Alumni communications | ROPA-010 · Review overdue | Review the record and set its next review date. (ROPA-010) | Medium | P2 | Unassigned | Open | 2027-01-04 | 61–90 days | No | Open | Enabling control | 0 | 0

## Gaps
Source | Assessment or record | Area or register rule | Finding | Recommended fix | Severity | Priority | State | Penalty heads | Actions | Actions still owed
Assessment | Mumbai University DPDP Compass Baseline | Governance, accountability and DPDP ownership | Review and remediate: Is there a formally nominated DPDP owner or nodal officer? | Nominate DPDP owner and publish internal responsibility note. | Low | P3 | Open | Enabling control | 1 | 1
Processing register | Online admission application | ROPA-001 · No verifiable parental consent | No verifiable parental consent: ROPA-001 — Online admission application | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Online admission application | ROPA-001 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-001 — Online admission application | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · No verifiable parental consent | No verifiable parental consent: ROPA-002 — Examination registration and result processing | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-002 — Examination registration and result processing | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · No verifiable parental consent | No verifiable parental consent: ROPA-003 — Student ERP / SIS lifecycle management | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-003 — Student ERP / SIS lifecycle management | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · No verifiable parental consent | No verifiable parental consent: ROPA-004 — LMS learning activity | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-004 — LMS learning activity | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · No verifiable parental consent | No verifiable parental consent: ROPA-006 — Scholarship and concession processing | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-006 — Scholarship and concession processing | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · No verifiable parental consent | No verifiable parental consent: ROPA-007 — Affiliated college data exchange | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-007 — Affiliated college data exchange | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | AI student chatbot | ROPA-008 · No verifiable parental consent | No verifiable parental consent: ROPA-008 — AI student chatbot | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | AI student chatbot | ROPA-008 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-008 — AI student chatbot | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · No verifiable parental consent | No verifiable parental consent: ROPA-009 — Event and webinar registration | Obtain verifiable consent of a parent before processing a child's data (s.9(1), Rule 10), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · Children may be tracked or targeted | Children may be tracked or targeted: ROPA-009 — Event and webinar registration | Stop tracking, behavioural monitoring and targeted advertising of children (s.9(3)), or record the Fourth Schedule exemption that applies. | Critical | P0 | Open | Head 3 | 1 | 1
Processing register | Online admission application | ROPA-001 · No owner | No owner: ROPA-001 — Online admission application | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Online admission application | ROPA-001 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-001 — Online admission application | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Online admission application | ROPA-001 · Retention or erasure undecided | Retention or erasure undecided: ROPA-001 — Online admission application | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · No owner | No owner: ROPA-002 — Examination registration and result processing | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-002 — Examination registration and result processing | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Retention or erasure undecided | Retention or erasure undecided: ROPA-002 — Examination registration and result processing | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · No owner | No owner: ROPA-003 — Student ERP / SIS lifecycle management | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-003 — Student ERP / SIS lifecycle management | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Retention or erasure undecided | Retention or erasure undecided: ROPA-003 — Student ERP / SIS lifecycle management | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · No owner | No owner: ROPA-004 — LMS learning activity | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | LMS learning activity | ROPA-004 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-004 — LMS learning activity | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · Processor without a valid contract | Processor without a valid contract: ROPA-004 — LMS learning activity | Put a contract with DPDP and security clauses in place with each linked Data Processor (s.8(2), Rule 6(1)(f)). | High | P1 | Open | Head 1, Head 7 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · Retention or erasure undecided | Retention or erasure undecided: ROPA-004 — LMS learning activity | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · AI processing not reviewed | AI processing not reviewed: ROPA-004 — LMS learning activity | Review the AI or automated processing and approve the record. | High | P1 | Open | Head 4 | 1 | 1
Processing register | HR payroll and employee records | ROPA-005 · No owner | No owner: ROPA-005 — HR payroll and employee records | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | HR payroll and employee records | ROPA-005 · Retention or erasure undecided | Retention or erasure undecided: ROPA-005 — HR payroll and employee records | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · No owner | No owner: ROPA-006 — Scholarship and concession processing | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-006 — Scholarship and concession processing | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · Retention or erasure undecided | Retention or erasure undecided: ROPA-006 — Scholarship and concession processing | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · No owner | No owner: ROPA-007 — Affiliated college data exchange | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-007 — Affiliated college data exchange | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · Retention or erasure undecided | Retention or erasure undecided: ROPA-007 — Affiliated college data exchange | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | AI student chatbot | ROPA-008 · No owner | No owner: ROPA-008 — AI student chatbot | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | AI student chatbot | ROPA-008 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-008 — AI student chatbot | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | AI student chatbot | ROPA-008 · Retention or erasure undecided | Retention or erasure undecided: ROPA-008 — AI student chatbot | Record how long the data is kept, what ends it, and the law if one requires keeping it (s.8(7), Rule 8). | High | P1 | Open | Head 7 | 1 | 1
Processing register | AI student chatbot | ROPA-008 · AI processing not reviewed | AI processing not reviewed: ROPA-008 — AI student chatbot | Review the AI or automated processing and approve the record. | High | P1 | Open | Head 4 | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · No owner | No owner: ROPA-009 — Event and webinar registration | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-009 — Event and webinar registration | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Alumni communications | ROPA-010 · No owner | No owner: ROPA-010 — Alumni communications | Assign a named owner who is accountable for this processing activity. | High | P1 | Open | Enabling control | 1 | 1
Processing register | Alumni communications | ROPA-010 · Purpose or lawful ground undecided | Purpose or lawful ground undecided: ROPA-010 — Alumni communications | State the purpose, and choose the ground it relies on — consent or a legitimate use — for counsel to confirm. | High | P1 | Open | Head 7 | 1 | 1
Processing register | Online admission application | ROPA-001 · Vendor not mapped | Vendor not mapped: ROPA-001 — Online admission application | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Online admission application | ROPA-001 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-001 — Online admission application | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Online admission application | ROPA-001 · Review overdue | Review overdue: ROPA-001 — Online admission application | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Vendor not mapped | Vendor not mapped: ROPA-002 — Examination registration and result processing | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Consent capture not recorded | Consent capture not recorded: ROPA-002 — Examination registration and result processing | Record how consent is captured and how it can be withdrawn as easily as it was given. | Medium | P2 | Open | Head 7 | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-002 — Examination registration and result processing | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Examination registration and result processing | ROPA-002 · Review overdue | Review overdue: ROPA-002 — Examination registration and result processing | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Vendor not mapped | Vendor not mapped: ROPA-003 — Student ERP / SIS lifecycle management | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-003 — Student ERP / SIS lifecycle management | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Student ERP / SIS lifecycle management | ROPA-003 · Review overdue | Review overdue: ROPA-003 — Student ERP / SIS lifecycle management | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | LMS learning activity | ROPA-004 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-004 — LMS learning activity | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | LMS learning activity | ROPA-004 · Review overdue | Review overdue: ROPA-004 — LMS learning activity | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | HR payroll and employee records | ROPA-005 · Vendor not mapped | Vendor not mapped: ROPA-005 — HR payroll and employee records | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | HR payroll and employee records | ROPA-005 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-005 — HR payroll and employee records | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | HR payroll and employee records | ROPA-005 · Review overdue | Review overdue: ROPA-005 — HR payroll and employee records | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · Vendor not mapped | Vendor not mapped: ROPA-006 — Scholarship and concession processing | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-006 — Scholarship and concession processing | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Scholarship and concession processing | ROPA-006 · Review overdue | Review overdue: ROPA-006 — Scholarship and concession processing | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · Vendor not mapped | Vendor not mapped: ROPA-007 — Affiliated college data exchange | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-007 — Affiliated college data exchange | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Affiliated college data exchange | ROPA-007 · Review overdue | Review overdue: ROPA-007 — Affiliated college data exchange | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | AI student chatbot | ROPA-008 · Vendor not mapped | Vendor not mapped: ROPA-008 — AI student chatbot | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | AI student chatbot | ROPA-008 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-008 — AI student chatbot | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | AI student chatbot | ROPA-008 · Review overdue | Review overdue: ROPA-008 — AI student chatbot | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · Vendor not mapped | Vendor not mapped: ROPA-009 — Event and webinar registration | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-009 — Event and webinar registration | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Event and webinar registration | ROPA-009 · Review overdue | Review overdue: ROPA-009 — Event and webinar registration | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Alumni communications | ROPA-010 · Vendor not mapped | Vendor not mapped: ROPA-010 — Alumni communications | Link the Data Processors involved to the vendor register. | Medium | P2 | Open | Enabling control | 1 | 1
Processing register | Alumni communications | ROPA-010 · Rule 6 minimum safeguards not confirmed | Rule 6 minimum safeguards not confirmed: ROPA-010 — Alumni communications | Confirm each Rule 6 minimum safeguard is in place — encryption, access control, logs, backups, one-year log retention, organisational measures. | Medium | P2 | Open | Head 1 | 1 | 1
Processing register | Alumni communications | ROPA-010 · Review overdue | Review overdue: ROPA-010 — Alumni communications | Review the record and set its next review date. | Medium | P2 | Open | Enabling control | 1 | 1