## About
Gap & Action Tracker
Mumbai University
Organisation | Mumbai University
As of | 19 October 2026
Version | 1
Generated | 19 October 2026, 08:55 IST by Registrar (DPDP Programme Owner)
Report | Every gap and action from the assessment and the register, as a working file.
About this export
This report is a DPDP readiness and assessment output based on information, responses and evidence made available during the assessment. It is not a final legal opinion, statutory certification or guarantee of compliance. Final legal interpretation, policy approval and contractual sign-off should be reviewed by authorised legal counsel.
Notes
Actions: one row per remediation action, from the assessments and the processing register, labelled by source.
Gaps: one row per gap, with how many of its actions are still owed.
Penalty heads are those the gap counts against directly under the TrustStack exposure model; the window and Overdue are measured from today's date in India.
Every value is as stored when the file was generated; no cell holds a formula.

## Actions
Source | Assessment or record | Area or register rule | Action | Severity | Priority | Owner | Status | Due date | Roadmap window | Overdue | Gap | Penalty heads | Artefacts attached | Accepted artefacts | Closed on | Closed by | Closed on the basis of | Notes
Assessment | Mumbai University DPDP Compass Baseline | Governance, accountability and DPDP ownership | Nominate DPDP owner and publish internal responsibility note. | Low | P3 | Unassigned | Open |  | Next assessment cycle | No | Open | Enabling control | 0 | 0
Breach register | Examination marks list shared through a public link | BRH-2026-001 · Accidental disclosure | Review link-sharing settings on every examinations folder | High | P1 | MU IT/Security Lead | Open | 2026-11-30 | 31–60 days | No | Open | Head 2 | 0 | 0
Rights and grievance register | Grievance GRV-2026-001 | GRV-2026-001 · Grievance (s.13, Rule 14(3)) | Make corrections in the student record flow to the examination system | High | P1 | Controller of Examinations (Department Owner) | Open | 2026-12-15 | 31–60 days | No | Open | Head 7 | 0 | 0
Retention register | Retention of ROPA-009 | ROPA-009 · When the purpose is served (s.8(7)(a)) | Erase the February 2025 webinar registrations from the events mailing tool and the shared drive | High | P1 | MU IT/Security Lead | Open | 2026-11-15 | Next 30 days | No | Open | Head 7 | 0 | 0

## Gaps
Source | Assessment or record | Area or register rule | Finding | Recommended fix | Severity | Priority | State | Penalty heads | Actions | Actions still owed
Assessment | Mumbai University DPDP Compass Baseline | Governance, accountability and DPDP ownership | Review and remediate: Is there a formally nominated DPDP owner or nodal officer? | Nominate DPDP owner and publish internal responsibility note. | Low | P3 | Open | Enabling control | 1 | 1
Breach register | Examination marks list shared through a public link | BRH-2026-001 · Accidental disclosure | BRH-2026-001: Examination marks list shared through a public link |  | High | P1 | Open | Head 2 | 1 | 1
Rights and grievance register | Grievance GRV-2026-001 | GRV-2026-001 · Grievance (s.13, Rule 14(3)) | GRV-2026-001: Grievance (s.13, Rule 14(3)), received 2026-09-02 |  | High | P1 | Open | Head 7 | 1 | 1
Retention register | Retention of ROPA-009 | ROPA-009 · When the purpose is served (s.8(7)(a)) | Retention of ROPA-009: Erasure overdue, end date 2026-02-15 |  | High | P1 | Open | Head 7 | 1 | 1